## Sheet1
received 21th April, due 21th May
id | Status | Item | Actions | Response | Risk? | Mitigation Plan | Time Needed
1 | to do | As stated in the analysis plan of the protocol, heat vulnerability and liveability will be “determined from literature review using climate data from the Bureau of Meteorology”. It was unclear to the Committee how this stated method would develop the indicators of heat and vulnerability, therefore please update the protocol to elaborate upon and provide further details around how this will be done. | Hao to provide an explaination Update: Revise the paragraph and describe brifely how LST data is used to identify heatwaves (through EHF) and to derive HVI. |  | none | not needed | within a day
2 | to do | The Committee noted that the COD URF has been omitted from Section A of the Data Request/Application for Data. Please update. | Hao to confirm with Derrick if that's a mistake or intensional and the update accordingly Update: Clarify that we only need to use death registry (along with EDDC and APDC) for cohort identification, and CODURF is not needed here. |  | none | not needed | within a day
3 | to do | The Committee also noted that the study period includes the bushfire season of 2019-2020 and the lockdown periods during the COVID-19 pandemic. Please make comment on how the study will control for these potentially confounding factors. | Derrick to provide an strategy. (Hao and Derrick will think about it and come back to it in the meeting next week) | Study area (NSW) not significantly impacted by COVID lockdown. 2009 bushfire season is a noted anomaly. Omit Summer 2009 from the study. | Response is not acceptable | Hao will organize meetings with data scientists in AURIN, Stuart, and Melanie to discuss how to response | ~2-4 working days
4 | to do | The Committee queried whether the NSW APDC would be a reliable data source for information on underlying chronic health conditions. Please comment on whether this is intended to be the direct source for this information, or if it will be drawn from other datasets. Further, please elaborate upon how it will be determined whether an admission, presentation or death is heat related. | Derrick to provide an explanation. (Hao and Derrick will think about it and come back to it in the meeting next week) | testing/determining what this data can show is the purpose of the study. The information for chronic health conditions will be supplemented from the PHIDU (Prevalence of Chronic Diseases and Prevalence of Selected Health Risk Factors). We will conduct sensitivity analyses (cross-validation) comparing findings derived from APDC against PHIDU chronic health conditions to ensure validity and reliability of the data. | Response is not acceptable | same as above | ~2-4 working days
5 | to do | It was understood that the Spatial Smoothing Technique will be applied to reduce the risk of identifying communities or individuals, however it was unclear what factors will determine when it is appropriate to employ it. Subsequently, please update the protocol with information on the criteria that will be used to determine when it is appropriate to employ the Spatial Smoothing Technique. | Hao and Derrick to discuss and come up with an explaination. (ask Peter and AURIN data scientists) | According to the Statistical Spatial Framework guidance for Protecting Privacy for Geospatially Enabled Statistics through Geographic Differencing, "The region type selected for releasing data should have a large enough number of statistical units (e.g. persons or organisations) in each region to maintain confidentiality for the majority of the variables for which data is planned to be released. The size of the region must also be balanced against the regional analysis needs of the users of the data. Data confidentialisation techniques can then be used to manage the remaining instances where privacy risks exist." Spatial smoothing will be used as a last step when aggrgation cannot create large number still. 'we need to provide an answer to this point “however it was unclear what factors will determine when it is appropriate to employ it”. I am wondering if there is a rule of thumb we can use to state when spatial smoothing will be used? E.g. ‘when there are inconsistencies in the data, or less than x number of cases in an area, or in x types of conditions, spatial smoothing will be applied to ensure patient confidentiality and data quality.’ it is easy to identify personal records when there are fewer people living in that area. Maybe one strategy is to target the identifiable zone and replace the value by a mean or median value in a larger zone. read the SA1 data yourself first. You will have some good sense about how to deal with it. | Response is not acceptable | same as above | ~2-4 working days
6 | to do | Under Data Governance on page 13 of the protocol, the flow diagram indicates that in Stage 3 a risk analysis will occur. Please clarify whether this is the role of the expert panel on the AusUrb-HI project advisory committee (as referred to on page 18 of the protocol), as well as more broadly what it will entail. | Hao and Derrick to discuss how the advisory committee is going to do risk analysis Update: Yes; and they are going to look at our methodology to evaluate if there is a risk of reidentification. If it's about RI identifying individuals, it's not likely because none is based in NSW and none has been working in hospital or other health services. | Risk analysis done in both stage 3 (data custodian) and stage 4 (advisory committee looking at aggregated result). SURE custodian (before data is placed into SURE and when it is extracted – medium risk ), CHeReL (prior to data being put into SURE – medium risk), data custodian (before data is placed into SURE, when it is processed in SURE, and when it is extracted – medium risk), and the advisory committee (which will review aggregated results upon extraction from SURE – low risk). The one "risk analysis" reference in the diagram is oversimplified and misleading, so I'll remove it and explain the four layers instead. The data custodian/s will assess the disclosure risk of the outputs before they can be removed from SURE. | Response is not acceptable | same as above | ~2-4 working days
7 | to do | missing A) M5.1 HREA: please see attachment titled Health Liveability Study Areas with map and list of identified areas. | Hao will update the document | Study area (NSW) not significantly impacted by COVID lockdown. 2009 bushfire season is a noted anomaly. Omit Summer 2009 from the study. | none | not needed | within a day
8 | to do | missing B) Page 10 of protocol: excel file “study area geocodes”. | Hao will update the document |  | none | not needed | within a day
9 | to do | missing C) Page 10 of protocol: We have provided two files derived from the ABS that provide SA1 codes defining these urban regions: i. 2011 NSW significant urban area.xlsx ii. 2016 and 2021 NSW significant urban area.xlsx | Hao will update the document |  | none | not needed | within a day
10 | to do | missing D) Page 18 of protocol: the detailed analysis methodology plan of all the datasets and their integration into the overall health indicator is described in detail in the separately attached Analysis Plan document | Hao will update the document |  | none | not needed | within a day
11 | to do | missing E) Variables spreadsheet: In addition to the above, we also require SA1 codes for this study. The justification for requiring SA1 codes is provided in the attachment titled "Justification for SA1 data.docx" | Hao will update the document |  | none | not needed | within a day
12 | to do | The Committee acknowledged that the work from this study will result in an enduring data asset, and requested confirmation that any future research using the data asset will not proceed before ethics approval is obtained. | Hao to include an acknowledgement in response to the email |  | none | not needed | within a day
13 | Done | Please provide more information on the Cancer Determinants case study that has already received ethics approval (as referenced on page 7 of the protocol), including a copy of the protocol and approval from the reviewing HREC. | Hao to ask Peter/Kou Kou for the information Update: email sent and waiting for response; we will emphasize that the cancer one a different, separated case study with different state data, medical conditions, and led by different people. | The reference to the Cancer study was included in error and that the two studies are completely separate. | Peter/Kou Kou not responding within timeframe | follow up when needed | depdending on when Peter replies
14 | to do | Please ensure that all requests are submitted via REGIS by 5pm on the Monday. We are unable to review requests that are not submitted via REGIS. You should create and upload a cover letter to address each change made to the application and supporting documents. If you are changing any documents, ensure to update the footer with the new version and date and create a track changes version of each document to be uploaded with the submission. The electronic filename should include the word tracked and the version and date of the document can be included if preferable. | Hao will finalize and update |  | none | not needed | within a day