## Sheet1
| Case 1 - Urban Cancer Vulnerability Indicators | Qld |  |  | Case 2 - Heat Health Vulnerability | NSW |  | (Same as Case 3) | Case 3 - Integrating Liveability and Health Indicators
| Current Status | Change since last week | Weeks in current status | Comment | Current Status | Change since last week | Weeks in current status | Comment | Current Status | Change since last week | Weeks in current status | Comment
27/01/2022 |  |  |  |  | AURIN start preparing for CHeReL (data linkage) application. | N/A | N/A | As an action item from the steering committee meeting on 27th Jan. | (same as Case 2, same below) | (same as Case 2, same below) | (same as Case 2, same below) | (same as Case 2, same below)
14/3/2022 | PHA application first submitted. | N/A | N/A | N/A
30/03/2022 |  |  |  |  | First version of combined protocol application submitted to CHeReL along with supporting documents. | Preparing CHeReL application. | 9 | Application v1.0 is made. The most time consuming part is making contacts and gathering information.
31/3/2022 | [5 empty] | Waiting for CHeReL feedback. | within a week | First revision starts for CHeReL application (from v1.0 to v1.1).
22/4/2022 | Revision requested. | Waiting for feedback. | 6 weeks | N/A
26/05/2022 |  |  |  |  | REGIS application completed and submitted to NSW Population and Health Services Research Ethics Committee (PHSREC). | Preparing REGIS application. | 8 | Principle coordinating investigator added (Tracy). Independent review by Chayn from RMIT provided.
30/05/2022 |  |  |  |  | PHSREC replies and suggests to send REGIS application to CHeReL and quote REGIS reference number. Actions done in the same day. | Waiting for PHSREC feedback. | within a week | Hao taking over in the middle of preparing REGIS application.
2022-02-06 |  |  |  |  | CHeReL replies and confirms the documents are being reviewed before a technical feasibility letter can be issued. Then the application will be sent to Data Custodians. | Waiting for CHeReL feedback. | within a week | Both CHeReL application documents and REGIS application documents are sent to CHeReL.
15/06/2022 | Revised version resubmitted. | Preparing revision | 8 weeks | N/A
2022-08-07 |  |  |  |  | CHeReL requests for revision. | Waiting for CHeReL feedback. | 5 | There are two rounds of revision, and the second one is minor.
22/07/2022 |  |  |  |  | Revision cycles are done and final documents are submited. | Preparing CHeReL application revision. | 2 | After the revision cycles, application v1.2 final is created as a result and sent to CHeReL.
25/07/2022 |  |  |  |  | Technical feasibility letter is obtained from CHeReL. Application is sent to Data Custodians for review and approval. | Waiting for CHeReL feedback. | within a week | Now waiting for Data Custodians' feedback.
2022-02-08 | Waiting on PHA approval for the data linkage and access application. | no change | 7 weeks | Once obtained, the cancer case study group will then request the data custodians carry out the data linkage. | Got approval from Data Custodian for RBDM Deaths and COD URF. | Waiting for approval for NSW APDC and EDDC. | 1 week | Need to get all approvals before submitting to NSW PHSREC as the second step of application.
2022-09-08 | same as last week | no change | 8 weeks |  | same as last week | N/A | 2 weeks
16/08/2022 | same as last week | no change | 9 weeks |  | same as last week | N/A | 3 weeks
23/08/2022 | same as last week | no change | 10 weeks |  | APDC and EDDC Data Custodian request meeting to discuss some aspects of the project. | CHeReL replied with request from the data custodian. | within a week | Meeting will be held on 23th Aug, 2-3pm AEST.
2022-01-09 | same as last week | no change | 11 weeks |  | Finished data custodian meeting and internal project case study meeting. Currently working on action items for revising the application. | The requested data custodian meeting was finished. | within a week | Main action items: provide justification for the need of linked health data; provide supporting documentation (e.g., experience working with linked data, and similar research using linked data); and others.
2022-07-09 | same as last week | no change | 12 weeks |  | Set up weekly application progress meeting. Revising the application. | Working on action items for revising the application. | 2 weeks
13/09/2022 | same as last week | no change | 13 weeks |  | same as last week | Preparing revision | 3 weeks | Follow up meeting with Matt Beaty on 13th; Follow up methodology meeting with Stuart on 15th.
21/09/2022 | same as last week | no change | 14 weeks |  | same as last week | Preparing revision | 4 weeks | Draft change made. Starting cycles of review.
27/09/2022 | same as last week | no change | 15 weeks |  | Material prepared and ready to be reviewed by the steering committee before resubmission. | Steering committee discussed detailed methodology and justifications. | 5 weeks | content: detailed analysis methodology; justification for accessing linked health data; relevant research experience and publications
2022-04-10 | same as last week | no change | 16 weeks |  | same as last week | Preparing revision | 6 weeks | Draft to be sent for review (Melanie, Stuart, David)
2022-12-10 |  | Peter has sent a request email to PHA asking for update. | 17 weeks |  | same as last week | Preparing revision | 7 weeks
20/10/2022 | PHA approval obtained | no change | N/A |  | same as last week | Preparing revision | 8 weeks | Slowed by team member joining conference
27/10/2022 | waiting for data | Peter has forwarded details of the PHA approval to the QLD SSB on the 14th October. They are now waiting on the data to be provided from the other data custodians. | 1 week |  | same as last week | Preparing revision | 9 weeks
2022-03-11 | same as last week | no change | 2 weeks |  | same as last week | Preparing revision | 10 weeks
2022-10-11 | same as last week | no change | 3 weeks |  | same as last week | Preparing revision | 11 weeks
17/11/2022 | same as last week | no change | 4 weeks |  | application to be sent for review by the end of this week | application documents revision finished | within a week
24/11/2022 | same as last week | no change | 5 weeks |  | same as last week | waiting for feedback | 1 week
2022-01-12 | same as last week | no change | 6 weeks |  | same as last week | waiting for feedback | 2 week | David feedback received. Expect to resubmit before Christmas.
2022-08-12 | same as last week | no change | 7 weeks |  | same as last week | revision | 1 week | Working on David's feedback.
15/12/2022 | same as last week | no change | 8 weeks |  | application resubmitted | waiting for custodian feedback | within a week | will resubmit today after meeting with David
21/12/2022 | same as last week | no change | 9 weeks |  | waiting for data custodian feedback/approval | application was resubmitted last week | 2 week
2023-05-01 | same as last update | no change | 11 weeks |  | same as last update | N/A | 3 week
2023-12-01 | same as last update | no change | 12 weeks |  | same as last update | received clarification requests from CHeReL. | 1 week | Clarifications resubmitted.
19/1/2023 | same as last update | no change | 13 weeks |  | same as last update | waiting for feedback | 2 week | CHeReL sent the documents to the data custodian
26/1/2023 | same as last update | no change | 14 weeks |  | same as last update | no change | 3 week
2023-02-02 | same as last update | no change | 15 weeks |  | same as last update | no change | 4 week
2023-09-02 | same as last update | no change | 16 weeks |  | same as last update | no change | 5 week
16/2/2023 | same as last update | no change | 17 weeks |  | asked CHeReL to update with the data custodian. CHeReL has sent the update email. | waiting for feedback | 6 week
22/2/2023 | same as last update | no change | 18 weeks |  | waiting for APDC and EDDC data approval | Obtained approval for RBDM-deaths and COD-URF data. | within a week
2023-02-03 | same as last update | no change | 19 weeks |  | same as last update | waiting for feedback | 2 week
2023-09-03 | same as last update | no change | 20 weeks |  | same as last update | no change | 3 week
16/3/2023 | same as last update | no change | 21 weeks |  | same as last update | no change | 4 week
23/3/2023 | same as last update | no change | 22 weeks |  | same as last update | no change | 5 week
30/3/2023 | Hao waits for Peter's reply | Peter asked Hao for AURIN data. Hao is confirming the required data with Peter before sending it. | within a week |  | Hao and Flavia are working on getting the full approval as well as submitting the ethics application. | Conditional data custodian approval obtained. | within a week
2023-06-04 | same as last week |  | 1 week |  | 1. waiting the ethics application to be reviewed on 12th April 2. Aaron is working on getting the restricted datasets | 1. ethics application submitted 2. Hao asked Aaron about the progress of getting the restricted AURIN data. | within a week
13/4/2023 | Hao is waiting for any additional request from Peter. | Peter confirmed, and AURIN data was sent. | within a week |  | 1. waiting the ethics approval result 2. Aaron is working on getting the restricted datasets 3. Hao and Flavia working on getting the rest of AURIN data | Hao and Flavia started working on getting the rest of the AURIN data. | 1 week
20/4/2023 | Hao is waiting for any additional request from Kou Kou. | Kou Kou asked for additional data (and LGA data) as well as for help for data processing/comprehension. Hao addressd the requests. | within a week |  | same as last week |  | 2 week
27/4/2023 | same as last week |  | 1 week |  | Hao is working on ethics application revision. |  | within a week
2023-04-05 | same as last week |  | 2 week |  | Waiting for the ethics approval result | Ethics application revision submitted | within a week
2023-11-05 | same as last week |  | 3 week |  | same as last week |  | 1 week
18/5/2023 | same as last week |  | 4 week |  | waiting for CHeReL's response for clarification | Ethics approval obtained. Research governance authorisation requested. | within a week
25/5/2023 | received the linked data extract file for the cancer case study | waiting on data dictionaries from each of the data custodians to enable that data cleaning to start | within a week |  | waiting for data linkage | confirmed that research governance authorisation is not needed from the CINSW side. | within a week
2023-01-06 | same as last week |  | 1 week |  | working on AURIN data preprocessing |  | 1 week
2023-08-06 | same as last week |  | 2 week |  | same as last week |  | 2 week
15/06/2023 | same as last week |  | 3 week |  | same as last week |  | 3 week
22/06/2023 | same as last week |  | 4 week |  | same as last week |  | 4 week
30/06/2023 | same as last week |  | 5 week |  | same as last week |  | 5 week
2023-06-07 | same as last week |  | 6 week |  | same as last week |  | 6 week
13/07/2023 | all required datasets have been obtained, data analysis started |  | within a week |  | CHeReL checking with data custodian about the correctness of the variable spreadsheet. Linked health data is likely to be available by the end of the month |  | within a week
20/07/2023 |  |  |  |  | same as last week |  | 1 week
27/07/2023 |  |  |  |  | CHeReL asked for signing confidentiality agreement |  | within a week
2023-03-08 |  |  |  |  | waiting for the linked health data to be delivered | agreements sent; SURE training completed for Hao | within a week
2023-11-08 |  |  |  |  | same as last week |  | 1 week
17/08/2023 |  |  |  |  | same as last week |  | 2 week
23/08/2023 |  |  |  |  | SURE ready and linked health data begin to upload |  | within a week
31/08/2023 |  |  |  |  | same as last week |  | 1 week
2023-07-07 |  |  |  |  | CHeReL confirmed to upload health data in the next coming days |  | within a week
14/07/2023 |  |  |  |  | Data uploaded to SURE, awaiting approval by the curators |  | within a week
21/07/2023 |  |  |  |  | same as last week |  | 1 week
28/07/2023 |  |  |  |  | Hao has become the SURE curator. Linked health data approved and load into SURE workspace. |  | within a week
(end of the data acquisition update) |  |  |  |  | (end of the data acquisition update)
Suggested Status
Ethics submitted
Ethics signed off
Data custodian submitted
Data custodian signed off
Data linkage submitted
Data linkage released
Transfer data to SURE